MediTrack

Electronic Medical Record for a Multi-Speciality Hospital Group

Estimation Report

COCOMO effort, duration and staffing · mode justification · Brooks's Law check · what the model does not capture

| Case study | Case Study no. 1 – MediTrack (Aarogya Healthcare) |
| --- | --- |
| Course | Software Engineering & Project Management – B.Tech CSE 2025-29, Semester III |
| Institution | School of Future Tech, ITM Skills University |
| Team / roll numbers | [ to be filled in by the team ] |
| Version / date | 1.0 – October 2026 |

# 1. Purpose and inputs

This report estimates the effort, duration and average staffing of MediTrack using COCOMO, defends the result against the CFO's 18-month ceiling, and states clearly what the model does not capture. Its figures feed the Project Plan (WBS, Gantt chart, resource histogram), the Risk Register and the BRD cost section.

## 1.1 Given project data (used unchanged)

| Input | Value | Source |
| --- | --- | --- |
| Estimated size | 46 KLOC (46,000 lines of code) | Case study |
| Team experience | Medium-experienced | Case study |
| Domain | Regulated clinical workflow; safety-sensitive | Case study |
| Legacy migration volume | 2.4 million patient rows; about 7 % (≈ 168,000) malformed or duplicate | Case study |
| Schedule ceiling | 18 months | CFO |
| Quality targets | DRE ≥ 92 % before go-live; MTBF 1,400 h; MTTR 2 h | Case study |

Anything else in this report (allowances for migration review, training and so on) is a team assumption, and is labelled as one.

# 2. Choosing the COCOMO mode

Basic COCOMO has three modes. The mode changes the constants in the formulas and therefore the answer, so it must be argued from the project's characteristics, not picked for a convenient result.

| Characteristic (Boehm) | Organic | Semi-detached | Embedded |
| --- | --- | --- | --- |
| Team | Small, experienced, familiar with the problem | Medium size, mixed experience | Any size; works within tight constraints |
| Requirements | Flexible, few constraints | Mix of rigid and flexible requirements | Rigid; hardware, regulation and operations constrain the design |
| Environment | Familiar, stable | Some unfamiliar elements | Complex, tightly coupled to hardware / real-time operation |
| Typical example | Small business application | Transaction-processing or database systems | Flight control, real-time embedded control |

## 2.1 Decision: Semi-detached

- Team: medium-experienced. The case study says exactly this. It is neither the small expert team of the organic mode nor a specialist team working to rigid constraints.

- Mixed requirements. Part of MediTrack is rigid and safety-critical: the allergy gate, versioned records, the append-only audit trail and migration reconciliation (SRS FR-03, FR-04, FR-06, FR-12, NFR-02). Part is flexible: search, notes, lab results, discharge-summary layout, the fixed user interface. That mixture is the definition of semi-detached.

- Why not organic. The system is regulated and legally audited, the size is 46 KLOC, and the team is only medium-experienced. Organic would give about 134 person-months and would understate the cost of safety verification.

- Why not embedded. Embedded mode is meant for software bound tightly to hardware and real-time operation. MediTrack runs on commodity servers and browsers (UML Package, Fig. UML-5). Its regulatory strictness is real, but it is handled as a verification and risk matter (clinical-safety gate, rule packs in CI, DRE ≥ 92 %), and by keeping interaction rules as data rather than code (NFR-08). Embedded would give about 356 person-months and an average team of about 22, which the case study's team description does not support.

What would change the decision: if the hospital group asked for medical-device behaviour (real-time monitoring, device integration) or the team were found to be mostly inexperienced, the embedded constants would be reconsidered. This is carried to the Risk Register as an estimation-risk trigger.

# 3. Basic COCOMO calculation

Basic COCOMO: Effort E = a × (KLOC)^b person-months; Duration T = c × E^d months; Average staffing N = E ÷ T.

## 3.1 Working for the chosen mode (semi-detached: a = 3.0, b = 1.12, c = 2.5, d = 0.35)

| Step | Calculation |
| --- | --- |
| Size | S = 46 KLOC |
| Effort | E = 3.0 × 46^1.12 = 3.0 × 72.8 = 218.5 person-months |
| Duration | T = 2.5 × 218.5^0.35 = 2.5 × 6.59 = 16.5 months |
| Average staffing | N = 218.5 ÷ 16.5 = 13.3 people |
| Productivity | 46,000 LOC ÷ 218.5 PM = 211 LOC per person-month (about 2.5 KLOC per person-year) |

## 3.2 All three modes for comparison

| Mode | Effort (PM) | Duration (months) | Avg staff | LOC / PM | Use |
| --- | --- | --- | --- | --- | --- |
| Organic | 133.7 | 16.1 | 8.3 | 344 | Lower bound |
| Semi-detached | 218.5 | 16.5 | 13.3 | 211 | Chosen |
| Embedded | 356.1 | 16.4 | 21.7 | 129 | Upper bound |

Notice that the mode barely changes the duration (about 16 months in every mode) but changes the effort and team size by a factor of nearly three. The mode decision is therefore mostly a cost and staffing decision, which is why it needed an argument.

Sanity check on productivity. 211 LOC per person-month is within the range usually quoted for medium-size business systems and is higher than for the safety-critical embedded mode (129), as expected.

# 4. Defending the estimate against the 18-month ceiling

The nominal COCOMO duration (16.5 months) is below 18, but it is not the whole project. Basic COCOMO covers product design through integration and test; it excludes the plans-and-requirements phase that comes before. A simple add-up therefore reaches the ceiling with nothing to spare:

| Item | Months | Comment |
| --- | --- | --- |
| Plans and requirements phase | 1.5 | Team allowance (about 10 % of the development duration); covers BRD, SRS, UML, plan. |
| COCOMO development duration (nominal) | 16.5 | Product design to integration and test. |
| Sequential total | 18.0 | Zero schedule reserve – unacceptable for a project with a migration and 27 sites. |

## 4.1 Recommended response: planned schedule compression from day one

The SRS already commits to a 6-week schedule reserve inside the 18 months. To create it, the development schedule is compressed to 15.0 months, which is 91 % of nominal. Boehm's Intermediate COCOMO prices schedule compression through the SCED driver: compressing to 85 % of nominal costs a factor of 1.08 in effort. Interpolating linearly for 91 %:

| Step | Calculation |
| --- | --- |
| Compression ratio | 15.0 ÷ 16.5 = 0.91 |
| Effort multiplier | 1 + (1 − 0.91) ÷ (1 − 0.85) × 0.08 = 1.048 |
| Baseline effort | 218.5 × 1.048 = 228.9 person-months |
| Baseline staffing | 228.9 ÷ 15.0 = 15.3 people on average |
| Feasibility | Boehm's limit: a project cannot be compressed below about 75 % of nominal (here 12.4 months). 91 % is well inside the feasible range. |

Figure E-1  Schedule budget: sequential nominal plan versus the recommended baseline with a 1.5-month (6-week) reserve.

Result: 1.5 + 15.0 + 1.5 = 18.0 months. The ceiling is met with a 6-week reserve, at the price of about 5 % more effort and about two more people than the nominal plan. Because the extra people are in the team from the start, this is planned compression, not the late staffing increase that Brooks's Law warns against (section 6).

# 5. Baseline effort and staffing profile

The effort is split across the three COCOMO phases using a planning split of 17 % design, 64 % programming (including unit test) and 19 % integration and test, informed by Boehm's phase distribution. Schedule is split 25 % / 50 % / 25 % as a team planning assumption. The Project Plan's resource histogram uses these figures.

| Phase | Effort share | Effort (PM) | Duration (months) | Average staff |
| --- | --- | --- | --- | --- |
| Product design | 17 % | 38.9 | 3.8 | 10.4 |
| Programming and unit test | 64 % | 146.5 | 7.5 | 19.5 |
| Integration and system test | 19 % | 43.5 | 3.8 | 11.6 |
| Total | 100 % | 228.9 | 15.0 | 15.3 (average) |

The programming phase peaks at about 20 people. To keep communication manageable, the team is organised into four squads of about five (clinical core; prescribing and safety; lab, pharmacy and discharge; platform, security, audit and migration), plus a quality group that reports independently to the project manager.

# 6. Sanity check against Brooks's Law

Brooks's Law: adding people to a late software project makes it later, because new people need training and the number of communication paths grows as n(n − 1) ÷ 2. Three checks:

| Check | Numbers | Conclusion |
| --- | --- | --- |
| Can we simply buy time with people? (target 12 months) | 218.5 ÷ 12 = 18.2 people; the COCOMO limit is 12.4 months | Not feasible: 12 months is below the 75 % limit, and the team would almost double. |
| Communication paths | 13 people: 78 · 15: 105 · 20: 190 | Paths grow faster than headcount (13 → 20 is +54 % people, +144 % paths), hence the squad structure. |
| Late rescue: add 5 people at month 9 of 15 | 15 → 20 people; paths 105 → 190 (+81 %); new people need weeks of ramp-up | Not a valid recovery plan. Recovery is by scope control (MoSCoW) and the reserve, not headcount. |
| Is the baseline compression Brooks-safe? | Staff added from month 1; 91 % of nominal schedule | Yes: planned early, inside the feasible range. |

Brooks's rule of thumb for time allocation (about one-third planning, one-sixth coding, one-half testing) says testing deserves far more time than coding. The planning rule for MediTrack is that verification activities (unit, integration, system, migration dry runs, and the safety gate) take roughly 40 % or more of the effort. This is detailed in the Test Plan and Project Plan.

# 7. What COCOMO does not capture

Basic COCOMO estimates only the development of the 46 KLOC product. The case study explicitly asks us to say what it leaves out. The table gives each omission, whether it is on the critical path, and an indicative allowance (team assumption) so that the omission is visible rather than ignored.

| Not captured | Why it matters for MediTrack | Allowance (assumption) | Who does it |
| --- | --- | --- | --- |
| Plans and requirements phase | Excluded from Basic COCOMO; covers BRD, SRS, UML, UI, plan. | 8 % × 218.5 = 17.5 PM | Project team |
| Migration engineering | Extract, transform and load tools, quarantine store, three dry runs and reconciliation for 2.4 M rows. | 12 PM | Project team (platform squad) |
| Migration data review | About 168,000 malformed or duplicate rows need a person to decide. At 3 min a row: 168,000 × 3 ÷ 60 = 8,400 h ÷ 140 h per PM = 60 PM (range 40–100 PM for 2–5 min a row). | 60 PM (hospital staff) | Data stewards at the hospitals; not the dev team |
| Training and go-live support | 20-minute nurse training plus role training at 27 sites; floor-walking at go-live. | 27 sites × 5 trainer-days = 135 days ÷ 21 = 6.4 PM | Training team |
| Clinical content | Formulary limits and interaction rules from the P&T committee (SRS A-2). | Not sized; dependency | P&T committee |
| Infrastructure and licences | Data centres, standby, VPN, backup vault, scanners. | Not sized; priced by IT | IT / procurement |
| Hardware procurement lead times, vendor delays | Can delay site roll-out. | Covered by reserve and the Risk Register | IT / procurement |

| Programme effort summary | Person-months | Notes |
| --- | --- | --- |
| Development (baseline, compressed) | 228.9 | Section 5 |
| Plans and requirements | 17.5 | Allowance |
| Migration engineering | 12.0 | Allowance |
| Training and go-live support | 6.4 | Allowance |
| Project-team total | 264.8 | ≈ 265 PM |
| Hospital data-steward review | 60.0 | Outside the project team; range 40–100 |

The migration and training items run in parallel tracks by separate people and are not on the development critical path, which is why they do not extend the 15-month development schedule. The data-steward review does need clinical staff to be released from their normal work, and is an explicit dependency in the Project Plan and Risk Register.

# 8. Model uncertainty and sensitivity

## 8.1 Size sensitivity (semi-detached, nominal)

| Case | Size (KLOC) | Effort (PM) | Duration (months) | Average staff |
| --- | --- | --- | --- | --- |
| −20 % | 36.8 | 170.2 | 15.1 | 11.3 |
| −10 % | 41.4 | 194.2 | 15.8 | 12.3 |
| Estimate | 46.0 | 218.5 | 16.5 | 13.3 |
| +10 % | 50.6 | 243.1 | 17.1 | 14.2 |
| +20 % | 55.2 | 268.0 | 17.7 | 15.1 |

A 20 % size overrun adds about 1.2 months to the nominal duration, which is within the 1.5-month reserve but leaves almost nothing for anything else. Size growth is therefore watched through the MoSCoW rule: Could, then Should, never Must.

## 8.2 Intermediate COCOMO downside scenario

The case study requires the Basic model, and the baseline above uses it. A more detailed Intermediate rating is a useful warning, though. Rating required reliability as very high (1.40), database size as high (1.08) and product complexity as high (1.15), and everything else nominal for a medium-experienced team, gives an effort adjustment factor of 1.40 × 1.08 × 1.15 = 1.74. Effort becomes 379.9 PM, duration 20.0 months and staffing about 19.0 people.

Reading of this result. It does not replace the baseline, but it tells us the baseline is optimistic if the safety and data drivers hurt as much as the model says, putting the 18-month ceiling at risk by about two months. We respond in three ways, all recorded in the Risk Register: (1) an estimation-risk entry with a trigger, namely effort more than 10 % over plan in two consecutive monthly reviews; (2) the pre-agreed scope-control rule; (3) early escalation to the CFO with a re-baseline decision rather than late surprise. The CFO should be told this now, not at month 12.

# 9. Cost conversion

The case study gives no salary or budget figure, so no rupee amount is asserted. Cost is obtained by multiplying person-months by an agreed loaded monthly rate:

| Item | Person-months | Cost |
| --- | --- | --- |
| Project team (baseline total) | ≈ 265 | ≈ PM × [ loaded rate – to be supplied by CFO ] |
| Hospital data-steward review | ≈ 60 (40–100) | Internal staff cost; [ rate – to be supplied ] |
| Infrastructure and licences | – | [ to be priced by IT ] |
| Contingency | 6 weeks of schedule reserve | Equal to 1.5 months of the average team (≈ 23 PM) |

The contingency is calculated as 1.5 months × 15.3 people ≈ 23 person-months.

# 10. Summary of figures carried to other documents

| Figure | Value | Used in |
| --- | --- | --- |
| Mode | Semi-detached | Project Plan, Risk Register |
| Nominal Basic COCOMO | 218.5 PM · 16.5 months · 13.3 people | This report |
| Baseline (compressed) development | 228.9 PM · 15.0 months · 15.3 people | Project Plan (Gantt, histogram) |
| Schedule | 1.5 plans and requirements + 15.0 development + 1.5 reserve = 18.0 months | Project Plan, BRD, SRS (6-week reserve) |
| Peak team | About 20 (programming phase), in four squads | Resource histogram |
| Project-team effort including non-COCOMO items | ≈ 265 PM | BRD cost section |
| Data-steward effort | ≈ 60 PM (40–100) | Project Plan, Risk Register |
| Downside scenario | ≈ 380 PM · ≈ 20 months (Intermediate COCOMO) | Risk Register (estimation risk) |